## Sheet1
Sprint start number: |  | 1
Sprint Start Date: |  | 6 Oktober 2025
Project Name : |  | Sistem Reservasi Online Shaskin Beauty Care | [5 empty] | 2025 |  | 2025 |  | 2025 |  | 2025 |  | 2025 |  | 2025 |  | 2025 |  | 2025 |  | 2025 |  | 2025 |  | 2025 |  | 2025 |  | 2025 | 2026 | 2026
[8 empty] | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6 |  | Sprint 7 |  | Sprint 8 |  | Sprint 9 |  | Sprint 10 |  | Sprint 11 |  | Sprint 12 |  | Sprint 13 |  | Sprint 14
# | Aktivitas | Assigned To | Start | End | Status | % Done | Milestone | 06 Okt | 12 Okt | 13 Okt | 19 Okt | 20 Okt | 26 Okt | 27 Okt | 02 Nop | 3 Nop | 9 Nop | 10 Nop | 16 Nop | 17 Nop | 23 Nop | 24 Nop | 30 Nop | 1 Des | 7 Des | 8 Des | 14 Des | 15 Des | 21 Des | 22 Des | 28 Des | 29 Des | 2025-01-04 | 2025-01-05 | 2025-01-11
1 | 1.1 Pembentukan Tim Proyek | Farros | 2025-10-06 | 2025-10-12 | Complete | 100%
2 | 1.2 Penentuan Tujuan dan Ruang Lingkup Sistem | Farros | 2025-10-06 | 2025-10-12 | Complete | 100%
3 | 1.3 Pengumpulan Data Awal dari Pihak Klinik (layanan, jadwal, pelanggan) | Farros | 2025-10-06 | 2025-10-13 | Complete | 100%
4 | 1.4 Penyusunan Jadwal dan Rencana Kegiatan | Farros | 2025-10-06 | 2025-10-20 | Complete | 100% | Project Initialization Completed
5 | 2.1 Wawancara dan Observasi Proses Reservasi Manual | Ridho | 2025-10-12 | 2025-10-26 | Complete | 100%
6 | 2.2 Identifikasi Masalah dan Kebutuhan Pengguna | Ridho | 2025-10-12 | 2025-10-26 | Complete | 100%
7 | 2.3 Analisis Data dan Alur Bisnis Klinik | Ridho | 2025-10-12 | 2025-10-19 | Complete | 100%
8 | 2.4 Pembuatan Document Final | Ridho | 2025-10-12 | 2025-11-09 | Inprogress | 50% | RD, SD, SRS Finalized
9 | 3.1 Perancangan Arsitektur Sistem | Zufrial | 2025-10-13 |  | Inprogress | 25%
10 | 3.2 Desain Struktur Database (MySQL) | Zufrial | 2025-10-13 |  | Inprogress | 25%
11 | 3.3 Desain Antarmuka Pengguna (UI/UX – Figma) | Zufrial | 2025-10-13 |  | Inprogress | 25%
12 | 3.4 Penyusunan Diagram (Use Case, Activity, ERD) | Zufrial | 2025-10-27 |  | Not Started | 0% | System Design Completed
13 | 4.1 Pengembangan Frontend (HTML, CSS, Bootstrap) | Andira |  |  | Not Started | 0%
14 | 4.2 Pengembangan Backend (PHP, MySQL) | Andira |  |  | Not Started | 0%
15 | 4.3 Integrasi Fitur Login dan Autentikasi | Andira |  |  | Not Started | 0%
16 | 4.4 Implementasi Modul Reservasi Online | Andira |  |  | Not Started | 0% | System Implementation Completed
17 | 4.5 Implementasi Modul Manajemen Layanan & Jadwal | Andira |  |  | Not Started | 0%
18 | 4.6 Implementasi Dashboard Admin dan Laporan | Andira |  |  | Not Started | 0%
19 | 5.1 Pengujian Fungsi Login dan Reservasi | Zufrial |  |  | Not Started | 0%
20 | 5.2 Pengujian Validasi Data dan Jadwal | Farros |  |  | Not Started | 0%
21 | 5.3 Pengujian Laporan dan Dashboard | Ridho |  |  | Not Started | 0%
22 | 5.4 Perbaikan Bug dan Optimasi | Andira |  |  | Not Started | 0%
23 | 6.1 Deploy Website ke Hosting dan Domain | Andira |  |  | Not Started | 0%
24 | 6.2 Konfigurasi Database dan Backup Awal | Andira |  |  | Not Started | 0%
25 | 6.3 Uji Coba Online Bersama Admin Klinik | All |  |  | Not Started | 0%
26 | 7.1 Penyusunan Panduan Pengguna (User Manual) | Ridho |  |  | Not Started | 0%
27 | 7.2 Penyusunan Panduan Admin dan Developer | Ridho |  |  | Not Started | 0%
28 | 7.3 Pelatihan Admin & Owner ShaSkin Beauty Care | All |  |  | Not Started | 0%
29 | 8.1 Evaluasi Bersama Pihak Klinik | Farros |  |  | Not Started | 0%
30 | 8.2 Monitoring Performa dan Kinerja Sistem | Ridho |  |  | Not Started | 0%
31 | 8.3 Pemeliharaan dan Update Fitur Secara Berkala | Andira |  |  | Not Started | 0%